[bookmark: At7Ch4]William J. Hughes Technical Center for Advanced Aerospace
Construction Qualified Vendor List (QVL) Competition 
Statement of Work
QVL-26-0024
AFTIL Relocation to Buildings 27 & 28, Phase 2
Attachment J-1


C.1	SCOPE OF WORK

The work includes the provision of all labor, materials, equipment, and incidental related work to reconfigure and upgrade spaces within Buildings 27 and 28 at the Federal Aviation Administration (FAA) William J. Hughes Technical Center for Advanced Aerospace (WJHTCAA). The reconfiguration will allow for the installation of simulators and associated hardware from the Airways Facilities Terminal Integration Lab (AFTIL).

Demolition:
· Remove vinyl wall base in Buildings 27 and 28 as per drawing set 201209.
· Remove chair rail trim and wall covering in Building 27 as per drawing set 201209.
· Remove walls in Building 28 as per drawing set 201209.
· Remove doors in Building 28 as per drawing set 201209.
· Remove wall mounted shelf in Building 28 as per drawing set 201209.
· Remove existing wall mounted tackable surfaces as per drawing set 201209.
· Remove light fixtures and associated track, occupancy sensors, and exit signage in Buildings 27 and 28 as per drawing set 201209.
· Remove ceiling grid and tiles in Buildings 27 and 28 as per drawing set 201209.
· Remove Wi-Fi routers and save for reinstallation in Buildings 27 and 28 as per drawing set 201209.
· Remove thermostat, control wiring, diffusers, ductwork, and hangers in Buildings 27 and 28 per drawing set 201209.
· Remove all floor tiles in Building 28 as per drawing set 201209. Save full tiles in good condition on 2’ x 2’ pallets for future re-use in other project. Approximately 1,000 tiles are expected to be suitable for saving.
· Remove sheetrock barrier underfloor in Building 28 as per drawing set 201209.
· Remove the offset flooring substructure in Building 28 as per drawing set 201209. Prioritize salvaging and reusing existing stanchions that are in good condition for this project (estimated at 80% reusable) 
· Remove all receptacles, junction boxes, whips, conduit, and pop-up receptacles in Building 28 as per drawing set 201209.

Flooring Installation:
· Reuse existing salvaged substructure components determined to be suitable for reuse. Provide and install new substructure components as necessary to complete the flooring system shown on Drawing 201209.
· Provide and install floor tiles in Building 28 as per drawing set 201209.
· Provide and install Koldlok or approved equal grommets in Building 28 as per drawing set 201209.
· All cutting of floor tiles must to be performed outside of the building.
· Contractor must ensure all substructure is level and stable with the surrounding floor system. Contractor is to verify each tile edge must be level with adjoining tile edges with a tolerance of 1/32”.

Electrical installation:
· Provide and install electrical panels as per drawing set 201209.
· Provide and install breakers as per drawing set 201209.
· Provide and install junction boxes, conduit, wiring, and receptacles as per drawing set 201209.
· Provide and install five (5) Uninterruptible Power Supplies (UPSs) and five (5) Power Distribution Units (PDUs) as per drawing set 201209.
· Provide and install polyvinyl chloride (PVC) piping for grounding wire as per drawing set 201209.
· Provide and install grounding plates and wiring as per drawing set 201209.
· Update all panel schedules upon project completion.

Lighting Installation:
· Provide and install temporary lighting consisting of LED lamps rated at a minimum of 1600 lumens per lamp. LED lamps must be installed on temporary lighting stringers with lamp holders spaced approximately 10’0” on center, prior to removing existing light fixtures.
· Provide and install new, permanent lighting fixtures as per drawing set 201209.
· Provide and install light switches and dimmers as per drawing set 201209.
· Provide and install occupancy sensors as per drawing set 201209.

Architectural Installation:
· Paint walls in Buildings 27 and 28 as per drawing set 201209.
· Install wall base in Buildings 27 and 28 as per drawing set 201209.
· Procure and provide chairs as per drawing set 201209.
· Infill wall opening in Building 28 as per drawing set 201209.
· Relocate door and frame in Building 28 as per drawing set 201209.
· Provide and install signage “NOT AN EXIT” in Building 28 as per drawing set 201209.
· Provide and install emergency exit signage throughout Buildings 27 and 28 as per drawing set 201209.

The Contractor must verify existing field conditions and dimensions prior to any fabrication or installation. If there are any discrepancies, the Contractor must notify the QVL Project TOR and/or Contracting Officer prior to proceeding with the work.


C.1.1 Key Personnel Requirements - 

This project requires badged key personnel for the following labor categories:

1. Field Superintendent/Site Safety and Health Officer (SSHO). The Position of Field Superintendent and SSHO can be filled by the same candidate. The Contractor must designate an alternate candidate for each labor category. Requirements for each labor category (including alternates) include:

· Minimum 5 years of supervisory experience with two (2) projects similar in size and scope to this project

· Must have completed and provide valid certificate for candidate’s 30- hour OSHA sponsored/approved course in Occupational Safety and Health Standards for Construction.

· The Field Superintendent/SSHO must be on-site at all times that work is being performed. Resumes and associated certificates must be submitted as a part of the Contractor’s submittals and approved prior to Notice to Proceed (NTP). Final approval of candidates is at the discretion of the Contracting Officer. 


The work is related to the following QVL categories: 

☒ 		Category 1 - General Construction
☐	Category 2 - Mechanical/HVAC-R
☐	Category 3 - Plumbing 
☐	Category 4 - Fire Protection and Suppression
☐ 	Category 5 - Electrical  
☐	Category 6 - Telecommunications 
☐	Category 7 - Roofing


C.2      SITE CONDITIONS – 

[bookmark: _Hlk196317040]BOA Clause 3.2.2.3-46 Supervising the Contract Work (July 2004)

At all times while the Contractor (you) performs this contract, and until you complete the work and FAA accepts it, you must directly supervise the work or assign and have on the worksite a competent supervisor who the Contracting Officer (CO) is satisfied with and who has authority to act on your behalf.


C.3	 SCHEDULE OF WORK

The Contractor must perform all work between the hours of 7:00 A.M. and 4:30 P.M. Monday through Friday (excluding Federal Holidays). 

Since the WJHTCAA is a secure facility, the Contractor must allow adequate time to clear personnel and equipment through the FAA Security Operations Center (SOC).

The Contractor must allow 15 work days throughout the duration of construction for the lab user to perform testing, when construction will not be permitted. Days may or may not be consecutive. The FAA will provide 14 days advance notice of any upcoming lab testing.


C.4	PERIOD OF PERFORMANCE

The period of performance will be 220 calendar days from the Notice to Proceed (NTP).


C.5	CONTRACT SPECIFICATIONS

[bookmark: _Hlk196317352]The contract specifications for this project, if not attached to this package, will be supplied in a separate attachment and will not be issued during the mandatory site visit. Contractors wishing to make notes on the specifications during the site visit must print and bring with them to the mandatory site visit. Regardless of how the specifications are distributed it will be the responsibility of the Contractor to confirm all specifications sections listed below have been received. 

SPECIFICATION SECTIONS – 

[bookmark: _Hlk196317402]01330 		Submittal Procedures 
TC-RD-6950-0120		General Specifications for Electrical Installations
FAA-STD-019G	Lightning and Surge Protection, Grounding, Bonding, and Shielding Requirements for Facilities and Equipment


[bookmark: _Hlk196310659]C.6	CONTRACT DRAWINGS – 

The contract drawings for this project, if not attached to this package, will be supplied in a separate attachment and will not be issued at the mandatory site visit. Contractors wishing to make notes on the drawings during the site visit must print and bring with them to the mandatory site visit. Regardless of how the contract drawings are distributed it will be the responsibility of the Contractor to confirm all contract drawings listed below have been received. The contract drawings are considered the property of the Government and must not be used for any purpose other than that contemplated by the specifications. The contract drawings indicate general arrangements, approximate sizes and relative locations of principal materials to be provided or tasks to be completed. Contract drawings are diagrammatic and are a graphic representation of contract requirements to best available standards at the scale used. The Contractor must provide offsets to clear interferences and supports which are not specifically shown, but which are obviously needed to make the system complete, operable, and safe. The Contractor must verify all elevations, dimensions and clearances at the site. The following contract drawings accompany the specifications and are a part thereof:


DRAWING LIST – AFTIL Relocation to Buildings 27 & 28, Phase 2

Drawing Number	Drawing Title

201209-G000		Cover Sheet
201209-A100		Equipment Floor Plan - Demolition - Second Floor - Building 27-2
201209-A101		Partition Wall Plan - New Work - Second Floor - Building 27-2
201209-A102		Equipment Floor Plan - New Work - Second Floor Building 27-2
201209-A103		Equipment Floor Plan - Demolition - First Floor - Building 28-1
201209-A104		Equipment Floor Plan - New Work - First Floor - Building 28-1
201209-A105		Reflected Ceiling Plans - Second Floor - Building 27-2  
201209-A106		Reflected Ceiling Plan - Demolition - First Floor - Building 28-1
201209-A107		Reflected Ceiling Plan - New Work - First Floor - Building 28-1 
201209-A108		Raised Access Floor Plan - Demolition - First Floor - Building 28-1 
201209-A109		Raised Access Floor Plan - New Work - First Floor - Building 28-1
201209-A901		Door Schedule, Notes and Details
201209-E001		Electrical General Notes
201209-E002		Grounding Standards
201209-E003		Lighting Notes and Legends
201209-E101		Underfloor Power Plan - Demolition - First Floor - Building 28-1
201209-E102		Underfloor Power Plan - New Work - First Floor - Building 28-1
201209-E103		Grounding Plans - New Work- First and Second Floor - Building 27
201209-E104		Grounding Plan - New Work - First Floor - Building 28-1 
201209-E105		Lighting Plan - Demolition - Second Floor - Building 27-2 
201209-E106		Lighting Plan - New Work - Second Floor - Building 27-2  
201209-E107		Lighting Plan - Demolition - First Floor - Building 28-1
201209-E108		Lighting Plan - New Work - First Floor - Building 28-1
201209-E601		Single Line Diagram and Panel Schedules
201209-E602		Panel Schedules - Bldg. 28-1
201209-E603		Panel Schedules - Bldg. 28-1
201209-E901		Electrical Details


C.7	SECURITY

The William J. Hughes FAA Technical Center for Advanced Aerospace is under security at all times. All critical areas (e.g. air traffic control towers) are controlled by means of a personal identification system. All personnel entering the facility will require a badge or visitor badge, which must be visible and worn at all times while on the premises. The Government will provide further instructions regarding security requirements at the time the badges are issued.


C.8	ADDITIONAL REQUIREMENTS AND CONSIDERATIONS – 


· [bookmark: _Hlk196317519][bookmark: _Hlk199333859]When applicable - The Government or the Government’s Center Operations and Maintenance Contractor’s (COM’s) Hazardous Waste Manager must review and sign any waste requiring: manifest, disposal paperwork or bill of lading, from this facility.
· When applicable - The Contractor must provide a minimum of 14 days’ written notice to the QVL Project TOR prior to scheduling any kind of Asbestos or Lead abatement work.
· The Contractor must restore any staging/laydown area, both inside and outside, to its previous condition after use. 
· The contractor must submit a Site-Specific Safety Plan that applies to this SOW. This plan is to serve as a supplement to the Contractor’s Corporate Safety Manual. The Site-Specific Safety Plan must address all definable features of work covered in the SOW and how safety will be addressed and enforced. (Note the Corporate Safety Manual was already submitted by the Contractor when they applied to be on the QVL.)
· The Contractor must maintain and submit a Daily Access Log of all personnel including; Prime Contractor employees, Subcontractor employees, Vendors, equipment, etc. that were on the site each day. 
· The Contractor must submit a Solid Waste Disposal Report each month to the Government. The report must include date of disposal, waste description, total weight of waste material in tons, total weight of waste material diverted, method of waste material disposal or diversion, and, if applicable, reasons why waste was not diverted.
· The Contractor must keep all equipment (i.e. ladders, job boxes, etc.), that is to remain on site in designated laydown areas and ensure it is properly labeled with the Contractor’s name.
· [bookmark: _Hlk198220845]The Contractor must coordinate with the QVL Project TOR prior to the start of any construction to document existing conditions and submit an existing condition report to the Government. 
· Note any/all photos must be taken in the presence of the QVL Project TOR and/or an authorized Government Representative.
· The Contractor must have a Dedicated Full Time Site Safety and Health Officer, and Field Superintendent (SSHO can be the same person).
· The Contractor must complete and submit two (2) “Record of Change Report” (RCR) forms for this project. The Government will supply the RCR form.
· The first RCR must be completed prior to, or during, demolition activities and must document all existing equipment, fixtures, devices, and building components being removed, demolished, relocated, salvaged, or otherwise taken out of service as indicated on the contract drawings. 
· If an item being removed or demolished does not have a manufacturer, model number, or serial number, the item must still be documented on the RCR with sufficient descriptive information to accurately identify the asset for Government records. 
· The second RCR must be completed following installation of all new equipment and building systems and submitted with the final Government closeout documents. The RCR must document all newly installed equipment, fixtures, devices, and systems, including manufacturer, model number, serial number, and other information required by the RCR form. 
· The Contractor is responsible for verifying the accuracy and completeness of all information provided on both RCR forms prior to submission to the QVL Project TOR.
· The Contractor must clean all work/construction areas after the end of each workday.
· The Contractor must dispose of all construction material.
· The Government will provide a staging area in Building 28 for the Contractor.
· The Contractor is responsible for equipment left on site
· The Contractor must place a 6 mil black or green plastic with grommet dust curtain around the construction area designated by the QVL Project TOR. The dust curtain must be installed floor to ceiling and secured at both ends so dust cannot get through.  
· The Contractor must place caution tape around the construction site.
· The Contractor must remove and dispose of all dust curtains and caution tape once construction is completed.
· [bookmark: _Hlk196317644]The Government will provide restrooms inside Buildings 27 and 28 for the Contractor to use.
· TEMPORARY UTILITIES - Pursuant to Contract Clause 3.2.2.3-55, "Availability and Use of Utility Services (July 2004)", the Government will make available reasonable amounts of the following utilities to the Contractor without charge: 
1. Domestic (Potable) Water
2. Electricity 


C.9      PROPRIETARY WORK – 

The Contractor must perform the following work in accordance with WJHTCAA standards and tied into existing monitoring stations; contact information is provided since a subcontracting arrangement is expected: 

Building Automation System (BAS):
Robert Koenig/Mike May
Tri-M Group
Cell: 610-496-4885/610-721-3540

Fire Protection Equipment Control & Monitoring System
Project Manager – Matthew Kennedy
The Hiller Companies
(484) 940-7150


C.10	SUBMITTALS

Pursuant to Contract Clauses 3.2.2.3-45, “Material and Workmanship (July 2004)” and 3.2.2.3-60, “Specifications, Drawings and Material Offers (July 2004)”, the Contractor must prepare and submit for government review and approval the construction submittals as specified in the contract specifications, herein this document, or as called for in the contract drawings.  Definitions, processing, required formats and required quantities for construction submittals are specified in project specification Section 01330, “Submittal Procedures”.     

a) Preconstruction Submittals:  As per the definition provided in specification Section 01330, “Submittal Procedures,” all preconstruction submittals are required within ten (10) days of contract award. 

b) The Government will schedule a mandatory Preconstruction Meeting once all preconstruction submittals have been received and approved. The Government expects to issue the Notice to Proceed (NTP) at this meeting, which starts the Period of Performance (POP). Note that issuance of the NTP may not take place until the Government has approved all preconstruction submittals.

c) The Contractor must submit the preconstruction submittals for Certificate of Insurance, Performance Bond, and Payment Bond directly to the Contracting Officer. The Contractor must submit all other preconstruction submittals to the QVL Project TOR tyler.wilk@faa.gov and cc to the QVL CORs coral.yip@faa.gov and kevin.scott@faa.gov

d) The Contractor must submit the following preconstruction submittals before the Government will issue Notice to Proceed: 

	Submittal #
	Submittal Description
	Due Date
	Reference

	1
	Performance Bond
	10 calendar days after award
	BOA Clause 3.4.1-4
& SOW C.10.c

	2
	Payment Bond
	10 calendar days after award
	BOA Clause 3.4.1-5
& SOW C.10.c

	3
	Certificate of Insurance
	10 calendar days after award
	BOA Clause 3.4.1-10
& SOW C.10.c

	4
	Schedule of Prices

	10 calendar days after award
	BOA Clause F.04

	5
	Contract Schedule
	10 calendar days after award
	*see note below

	6
	Site Specific Safety Plan
	10 calendar days after award
	BOA Clause H.14
& SOW C.8

	7
	Submittal Register
	10 calendar days after award
	Government Furnished

	8
	Field Superintendent
	10 calendar days after award
	SOW C.1.1

	9
	Site Safety and Health Officer
	10 calendar days after award
	SOW C.1.1



The Contract Schedule must indicate the Contractor’s planned sequence of work to complete the contract within the specified period of performance. The Contract Schedule must include activities for the following categories of work: 

(1) The sequence and schedule for:

(2)	At a minimum, the Contractor must identify and provide durations for the following work activities:
a.	Administrative work (e.g., submittals, procurement badging and fabrication lead times)
b.	Mobilization
c.	Demolition
d. 	Flooring Installation
e.	Electrical installation
g. 	Lighting Installation
h. 	Architectural Installation
i.	Clean up and punch list items
j.	Closeout 

(3)	If applicable, the Contract Schedule must specifically identify and differentiate between work activities planned for execution during regular work hours and work activities planned for execution outside of regular work hours. See paragraph titled “Schedule of Work” for specific requirements.

e) The Contractor must submit the following construction submittals during construction performance: 

	Submittal #
	Submittal Description
	Due Date
	Reference

	1
	Daily Inspection Reports
	Daily during construction
	BOA Clause F.08

	2
	Contract Discrepancy Reports
	Within 48 Hours of discovering a discrepancy
	BOA Clause F.08

	3
	Progress Photographs
All photos must be taken in the presence of the QVL Project TOR and/or authorized Government Representative
	At start of work, monthly with Contract Progress Report, and at completion of work
	BOA Clause F.10
& SOW C.8

	4
	Electronic Email
	Continuously
	BOA Clause G.04

	5
	Emergency Contacts – to include Primary and 1st tier Subcontractors. 
	To be submitted at or before Preconstruction meeting and updated as needed.
	BOA Clause H.02

	6
	Daily Access Log
	Daily during Construction
	SOW C.8

	[bookmark: _Hlk199071388]7
	Solid Waste Disposal Report 
	Monthly after NTP is issued
	SOW C.8

	
	Completed RCR Form for removed items
	Prior/during demolition
	SOW C.8



f) The Contractor must submit the following submittals upon completion of work: 

	Submittal #
	Submittal Description
	Due Date
	Reference

	1
	Equipment/ Product Warranty List
	At work completion
	BOA Clause F.11

	2
	As-built drawings
	At work completion
	BOA Clause F.11

	3
	Asbestos Free Statement
	At work completion
	BOA Clause 3.6.3-12

	4
	Installation/Operation & Maintenance Manuals for all equipment
	At work completion
	Drawing set 201209

	5
	Completed RCR Form for new items
	At work completion
	SOW C.8



